## 📋 Instructions
PROJECT TIMELINE GANTT CHART
Free Excel Template by XplorExcel.com ¦ Intermediate Level
HOW TO USE THIS TEMPLATE
Step 1 | Go to the '📊 Gantt Chart' sheet — this is your main working sheet.
Step 2 | Enter your project tasks in column B (Task Name) starting from row 6.
Step 3 | Enter the team member name in column C (Assigned To).
Step 4 | Enter the Start Date in column D and End Date in column E.
Step 5 | Column F (Duration) is auto-calculated — do not edit it.
Step 6 | Enter % progress in column G (e.g., type 0.75 for 75%).
Step 7 | Column H (Status) is auto-calculated using an IF formula.
Step 8 | Column I (Days Left) is auto-calculated — shows 0 if past due.
Step 9 | The Gantt bar area (columns K onwards) fills automatically with colour.
Step 10 | Update the project start date in cell K4 on the Gantt Chart sheet.
COLOUR CODING GUIDE
Green bar | Task is On Track — progressing within the deadline.
Red bar | Task is Delayed — deadline passed, not yet 100% complete.
Orange bar | Task is Completed — progress is marked at 100%.
Blue header | Today's date column — helps you see where you are in the project.
Grey | Future tasks — not yet started.
Check out our templates @ xplorexcel.com
KEY FORMULAS USED
Duration | End Date minus Start Date (formatted as Number, not Date)
Status | IF(Progress=1, Completed, IF(TODAY() greater than EndDate, Delayed, On Track))
Days Left | MAX(0, End Date minus TODAY()) — shows 0 if past due
Gantt Bar | AND(DateHeader >= StartDate, DateHeader <= EndDate) [used in Conditional Formatting]
Today Line | DateHeader equals TODAY() [used in Conditional Formatting on header row]
TIPS
Freeze Panes | Click cell K6 → View → Freeze Panes to keep task info visible while scrolling right.
Print Setup | Page Layout → Landscape → Fit to 1 page wide for clean printout.
Add Tasks | Insert rows between row 6 and the last task row. Copy formulas from adjacent row.
NETWORKDAYS | Replace =D-C with =NETWORKDAYS(C,D)-1 to exclude weekends from duration.
© XplorExcel.com ¦ For more free Excel templates visit xplorexcel.com

## 📊 Gantt Chart
PROJECT TIMELINE — GANTT CHART
XplorExcel.com ¦ Update your tasks, dates and progress below ¦ Gantt bars update automatically
Project Name: | Website Redesign Project | Total Tasks: | 12 | Overall Progress: | 816.7% | 2026-04-11
# | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Progress % | Status | Days Left | time axis 2026-04-01 to 2026-05-15
1 | Project Kickoff & Planning | Rahul Sharma | 2026-04-01 | 2026-04-05 | 4 | 100% | ✅ Completed | 0
2 | Requirements Gathering | Priya Mehta | 2026-04-03 | 2026-04-09 | 6 | 100% | ✅ Completed | 0
3 | UI/UX Wireframe Design | Amit Joshi | 2026-04-07 | 2026-04-15 | 8 | 80% | 🟢 On Track | 4
4 | Database Architecture | Suresh Kumar | 2026-04-09 | 2026-04-15 | 6 | 75% | 🟢 On Track | 4
5 | Frontend Development | Priya Mehta | 2026-04-13 | 2026-04-27 | 14 | 50% | 🟢 On Track | 16
6 | Backend Development | Suresh Kumar | 2026-04-13 | 2026-04-29 | 16 | 45% | 🟢 On Track | 18
7 | API Integration | Amit Joshi | 2026-04-23 | 2026-05-03 | 10 | 20% | 🟢 On Track | 22
8 | Content Writing & Upload | Neha Verma | 2026-04-19 | 2026-05-01 | 12 | 60% | 🟢 On Track | 20
9 | Quality Assurance & Testing | Rahul Sharma | 2026-04-29 | 2026-05-09 | 10 | 0% | 🟢 On Track | 28
10 | Bug Fixes & Optimization | Suresh Kumar | 2026-05-05 | 2026-05-11 | 6 | 0% | 🟢 On Track | 30
11 | UAT — User Acceptance Testing | Neha Verma | 2026-05-09 | 2026-05-13 | 4 | 0% | 🟢 On Track | 32
12 | Go Live & Deployment | Rahul Sharma | 2026-05-13 | 2026-05-15 | 2 | 0% | 🟢 On Track | 34
LEGEND
On Track — task is progressing within deadline
Delayed — deadline passed, task not yet complete
Completed — task is 100% done
Today — current date column
Not Started — task progress is 0%

## 📐 Formulas Guide
KEY FORMULAS — GANTT CHART TEMPLATE
Study these formulas to understand how the template works and to customize it.
FORMULA NAME | EXCEL FORMULA | EXPLANATION
Duration (Days) | 0 | Subtracts Start Date from End Date. Format result as Number, not Date.
Duration (Working Days) | -1 | Counts working days only — excludes Saturdays and Sundays.
Status (Auto) | 🔴 Delayed | Checks progress %. If 100% → Completed. If today > End Date → Delayed. Else → On Track.
Days Remaining | 0 | Days left before deadline. MAX(0,...) prevents negative numbers if past due.
Overall Progress | AVERAGE(H6:H17) — use in a summary cell above your task list | Average progress % across all tasks. Update range if you add more tasks.
Completed Tasks Count | 0 | Counts how many tasks are marked as Completed.
Delayed Tasks Count | 0 | Counts how many tasks are currently delayed.
On Track Tasks Count | 0 | Counts how many tasks are on track.
CONDITIONAL FORMATTING
Gantt Bar — On Track | FALSE | Fills cell green if the column date falls within task dates and task is not delayed.
Gantt Bar — Delayed | TRUE | Fills cell red if the column date is within task dates and deadline has passed.
Gantt Bar — Completed | FALSE | Fills cell teal/orange if task is 100% complete.
Today Column Highlight | FALSE | Fills the entire column blue where the header date equals today's date.
REFERENCE GUIDE
Mixed Reference — Row Lock | K$5 | $ before 5 locks the row. When formula copies down, it always refers to row 5 (date header).
Mixed Reference — Col Lock | $E6 | $ before E locks the column. When formula copies right, it always refers to column E (Start Date).
Why mixed references? | AND(K>=, K<=, <1, TODAY()<=) — used in Conditional Formatting, not as a regular formula | This is the most important concept in the Gantt CF formula. Row locked for dates, column locked for task data.

## 📝 Blank Template
PROJECT TIMELINE — GANTT CHART ¦ Blank Template
Fill in your project name, tasks, dates and progress. Gantt bars auto-update via Conditional Formatting.
Project Name: | [Enter your project name] |  | Start Date: | [date] | Progress: | 0%
# | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Progress % | Status | Days Left | time axis 2026-05-01 to 2026-06-14
1 |  |  |  |  | 0 |  | 🔴 Delayed | 0
2 |  |  |  |  | 0 |  | 🔴 Delayed | 0
3 |  |  |  |  | 0 |  | 🔴 Delayed | 0
4 |  |  |  |  | 0 |  | 🔴 Delayed | 0
5 |  |  |  |  | 0 |  | 🔴 Delayed | 0
6 |  |  |  |  | 0 |  | 🔴 Delayed | 0
7 |  |  |  |  | 0 |  | 🔴 Delayed | 0
8 |  |  |  |  | 0 |  | 🔴 Delayed | 0
9 |  |  |  |  | 0 |  | 🔴 Delayed | 0
10 |  |  |  |  | 0 |  | 🔴 Delayed | 0
11 |  |  |  |  | 0 |  | 🔴 Delayed | 0
12 |  |  |  |  | 0 |  | 🔴 Delayed | 0
13 |  |  |  |  | 0 |  | 🔴 Delayed | 0
14 |  |  |  |  | 0 |  | 🔴 Delayed | 0
15 |  |  |  |  | 0 |  | 🔴 Delayed | 0
16 |  |  |  |  | 0 |  | 🔴 Delayed | 0
17 |  |  |  |  | 0 |  | 🔴 Delayed | 0
18 |  |  |  |  | 0 |  | 🔴 Delayed | 0
19 |  |  |  |  | 0 |  | 🔴 Delayed | 0
20 |  |  |  |  | 0 |  | 🔴 Delayed | 0